TPM IMPLEMENTATION CHECKLIST

A step-by-step guide from baseline assessment to sustained results

Total Productive Maintenance  |  5 Phases  |  50+ Action Items

How to use this checklist: Work through each phase in sequence. Assign an owner and timing to each action item. Check off items as they are completed. This document is designed to be edited directly — add notes in the Owner 
and Timing columns as your programme progresses.

PHASE 1  |  FOUNDATION & BASELINE ASSESSMENT

Weeks 1–4  |  Leadership team + Maintenance Manager

Before any TPM activity begins, establish a clear picture of current equipment performance and organisational readiness. This phase sets the measurement baseline and secures the leadership commitment required 
to sustain the programme.

Leadership Alignment

ACTION ITEM

OWNER

TIMING

⃞

Appoint a TPM Programme Sponsor (senior plant leadership)

Plant Director

Week 1

⃞

Define TPM goals tied to business KPIs (OEE target, downtime reduction %)

TPM Sponsor

Week 1

⃞

Form TPM Steering Committee (Ops, Maintenance, Quality, HR)

TPM Sponsor

Week 2

⃞

Communicate TPM programme vision to all shifts and departments

Plant Director

Week 3

⃞

Allocate TPM budget and protected time for training activities

Plant Director

Week 2

Equipment & Performance Baseline

ACTION ITEM

OWNER

TIMING

⃞

List all production assets and classify by criticality (A/B/C)

Maintenance Mgr

Week 2

⃞

Measure current OEE for all Tier-A (critical) assets

Reliability Eng

Week 3

⃞

Document unplanned breakdown frequency and average duration 
(MTBF / MTTR)

Maintenance Mgr

Week 3

⃞

Categorise downtime events against the Six Big Losses framework

Reliability Eng

Week 4

⃞

Record current defect / scrap rates by asset and product

Quality Mgr

Week 3

⃞

Map existing maintenance activities against the 8 TPM pillars — identify gaps

TPM Sponsor

Week 4

⃞

Conduct workforce skills assessment for operators and technicians

HR / Training Mgr

Week 4

5S Workplace Foundation

ACTION ITEM

OWNER

TIMING

⃞

Complete 5S audit of all pilot area workstations and equipment zones

Ops Supervisor

Week 3

⃞

Implement Sort, Set in Order, Shine actions in pilot area

Ops Team

Week 4

⃞

Establish visual management standards (labelling, shadow boards, 
colour coding)

Ops Supervisor

Week 4

⃞

Document and photograph "before" state for programme baseline record

TPM Coordinator

Week 4

PHASE 2  |  TRAINING & CAPABILITY DEVELOPMENT

Weeks 3–8  |  HR, Training Manager + Maintenance team

TPM cannot function without a workforce that understands both the methodology and their expanded responsibilities. This phase builds the capability foundation for all subsequent TPM pillars — prioritise it even when production 
pressure is high.

Core TPM Training

ACTION ITEM

OWNER

TIMING

⃞

Deliver TPM fundamentals training to all operators (what is TPM, 8 pillars, 
their role)

Training Mgr

Week 4–5

⃞

Deliver basic maintenance principles training to operators 
(inspection, cleaning, lubrication)

Maint. Trainer

Week 5–6

⃞

Deliver reliability engineering training to maintenance technicians

Reliability Eng

Week 5–7

⃞

Train supervisors on TPM coaching techniques and team facilitation

Training Mgr

Week 6

⃞

Train quality team on Quality Maintenance pillar concepts and defect analysis

Quality Mgr

Week 7

Skills Matrix & Development Plans

ACTION ITEM

OWNER

TIMING

⃞

Build operator skills matrix — document current vs required competencies 
per asset

HR / Training Mgr

Week 6

⃞

Create individual development plans for operators and technicians

Supervisors

Week 7

⃞

Establish on-the-job coaching schedule (paired technician / operator sessions)

Maint. Supervisor

Week 8

⃞

Set up visual skills board on shop floor (T-card or digital skills tracker)

HR / Training Mgr

Week 8

Focused Improvement (Kaizen) Training

ACTION ITEM

OWNER

TIMING

⃞

Train cross-functional teams on root cause analysis (5-Why, Fishbone)

Reliability Eng

Week 7

⃞

Train team leads on problem-solving facilitation and Kaizen workshop format

Training Mgr

Week 8

⃞

Introduce OEE data collection and loss categorisation to all shift teams

Ops Supervisor

Week 7

PHASE 3  |  PILOT LAUNCH — AUTONOMOUS & PLANNED MAINTENANCE

Weeks 6–14  |  Operations + Maintenance teams

Launch TPM on a single asset or production line before rolling out plant-wide. The pilot builds proof of concept, surfaces implementation challenges, and generates the early results needed to sustain wider organisational momentum.

Select & Prepare Pilot Asset

ACTION ITEM

OWNER

TIMING

⃞

Select pilot asset — high OEE loss, high visibility, motivated operator team

TPM Steering

Week 6

⃞

Complete thorough initial cleaning (restore asset to basic condition)

Ops + Maint

Week 7

⃞

Identify and tag all deterioration points, leaks, wear items, and safety issues

Ops + Maint

Week 7

⃞

Photograph and document asset condition post-restoration

TPM Coordinator

Week 7

Autonomous Maintenance (AM) Launch

ACTION ITEM

OWNER

TIMING

⃞

Develop standardised AM task list (cleaning, inspection, lubrication points)

Maint. Engineer

Week 8

⃞

Create visual AM standards (one-point lessons, photo guides at asset)

Maint. + Ops

Week 8

⃞

Train assigned operators on AM tasks — sign off on competency

Maint. Trainer

Week 9

⃞

Issue operators with AM tools, supplies, and inspection checklists

Maintenance Mgr

Week 9

⃞

Launch daily AM routine — operator completes checklist each shift

Ops Supervisor

Week 10

⃞

Establish abnormality tag system (operators tag faults for maintenance action)

Ops Supervisor

Week 10

⃞

Review and close abnormality tags within agreed response time (SLA)

Maintenance Mgr

Ongoing

Planned Maintenance (PM) Launch

ACTION ITEM

OWNER

TIMING

⃞

Review OEM recommendations and failure history for pilot asset

Maint. Engineer

Week 8

⃞

Develop planned maintenance schedule (time-based and condition-based tasks)

Maint. Engineer

Week 9

⃞

Enter PM schedule into CMMS — assign work orders and responsible technicians

Maintenance Mgr

Week 10

⃞

Establish spare parts inventory for pilot asset critical components

Maintenance Mgr

Week 10

⃞

Execute first planned maintenance cycle — record actual vs planned time

Maint. Technician

Week 12

⃞

Track planned maintenance compliance rate weekly (target: >90%)

Maintenance Mgr

Ongoing

First Focused Improvement Project

ACTION ITEM

OWNER

TIMING

⃞

Analyse pilot asset OEE data — identify top-3 loss categories

Reliability Eng

Week 10

⃞

Launch first Kaizen project targeting highest-priority loss

Kaizen Team

Week 11

⃞

Conduct root cause analysis session (5-Why or Fishbone)

Kaizen Team

Week 12

⃞

Implement countermeasures and verify effectiveness with OEE data

Kaizen Team

Week 13–14

⃞

Document and standardise improvement — share learnings across facility

TPM Coordinator

Week 14

PHASE 4  |  PLANT-WIDE ROLLOUT & PILLAR EXPANSION

Months 4–12  |  All department leads

Expand proven pilot practices across all critical assets and begin activating the remaining TPM pillars. 
Maintain rigorous measurement cadence — OEE, MTBF, MTTR, and PM compliance — to guide priority setting 
and celebrate progress.

Asset Rollout

ACTION ITEM

OWNER

TIMING

⃞

Prioritise rollout sequence by asset criticality and OEE loss value

TPM Steering

Month 4

⃞

Replicate AM and PM programmes on all Tier-A assets

Ops + Maint

Month 4–8

⃞

Extend to Tier-B assets once Tier-A AM compliance exceeds 85%

TPM Steering

Month 8–12

⃞

Establish asset-level OEE dashboards visible to production teams

TPM Coordinator

Month 5

Quality Maintenance Pillar

ACTION ITEM

OWNER

TIMING

⃞

Map quality defects to specific equipment conditions and parameters

Quality + Maint

Month 4–5

⃞

Define critical equipment condition standards required for quality conformance

Quality Eng

Month 5

⃞

Establish PM tasks that verify equipment condition against quality standards

Maint. Engineer

Month 6

⃞

Integrate quality condition checks into AM operator inspection routines

Ops Supervisor

Month 6

⃞

Track defect rate per asset and trend against PM compliance rate

Quality Mgr

Ongoing

Early Equipment Management Pillar

ACTION ITEM

OWNER

TIMING

⃞

Create EEM input process — operators and technicians review capital 
project specs

Maint. Manager

Month 5

⃞

Develop maintainability checklist for new equipment commissioning sign-off

Reliability Eng

Month 6

⃞

Apply EEM review to all new capital equipment projects from Month 6 onwards

Engineering

Month 6+

TPM in Administration

ACTION ITEM

OWNER

TIMING

⃞

Map administrative processes that impact maintenance (spare parts PO, work order approval)

TPM Sponsor

Month 5

⃞

Apply Kaizen methodology to longest lead-time administrative bottlenecks

Admin + TPM

Month 6–8

⃞

Set SLA standards for work order processing, parts procurement, and PM scheduling

Plant Director

Month 7

Safety, Health & Environment Pillar

ACTION ITEM

OWNER

TIMING

⃞

Review all AM and PM procedures for safety risk — update where required

EHS Manager

Month 4

⃞

Implement near-miss reporting system linked to maintenance activities

EHS Manager

Month 5

⃞

Conduct monthly SHE audit of TPM work areas and report to steering committee

EHS Manager

Ongoing

⃞

Track lost-time incident rate and link to TPM programme scorecard

EHS Manager

Ongoing

PHASE 5  |  MEASUREMENT, REVIEW & CONTINUOUS IMPROVEMENT

Ongoing from Month 3  |  All levels of the organisation

Sustained TPM improvement requires a structured cadence of performance review, recognition, and continuous improvement activity. This phase does not end — it becomes the operating rhythm of a TPM-mature organisation.

Core KPI Tracking

ACTION ITEM

OWNER

TIMING

⃞

Measure and publish OEE weekly by asset and production line

Reliability Eng

Weekly

⃞

Report MTBF and MTTR monthly — trend over 6-month rolling window

Maintenance Mgr

Monthly

⃞

Track planned maintenance compliance rate weekly (target: >90%)

Maintenance Mgr

Weekly

⃞

Track autonomous maintenance compliance rate by asset and shift

Ops Supervisor

Daily

⃞

Monitor defect rate and scrap cost trend by asset

Quality Mgr

Weekly

⃞

Report lost-time incidents and near-misses linked to equipment

EHS Manager

Monthly

Review Cadence

ACTION ITEM

OWNER

TIMING

⃞

Daily shift handover review — AM completion, open abnormality tags, 
breakdown events

Shift Supervisor

Daily

⃞

Weekly maintenance and operations alignment meeting — PM compliance, 
top breakdowns

Ops + Maint Mgr

Weekly

⃞

Monthly TPM Steering Committee review — OEE trend, pillar status, 
Kaizen pipeline

Steering Cmte

Monthly

⃞

Quarterly deep-dive review — asset reliability analysis, training gap reassessment

TPM Sponsor

Quarterly

⃞

Annual TPM programme audit against JIPM criteria — identify next 
maturity goals

TPM Sponsor

Annual

Continuous Improvement Pipeline

ACTION ITEM

OWNER

TIMING

⃞

Maintain active Kaizen project pipeline — minimum 2 active projects per quarter

Kaizen Teams

Ongoing

⃞

Conduct focused improvement events (Kaizen blitz) for persistent 
high-loss categories

Kaizen Teams

Quarterly

⃞

Share improvement case studies across shifts and departments

TPM Coordinator

Monthly

⃞

Update AM and PM standards to reflect improvement countermeasures

Maint. Engineer

As required

⃞

Recognise and reward team and individual TPM contributions publicly

Plant Director

Monthly

TPM PERFORMANCE METRICS REFERENCE

Use these metrics to measure TPM impact and guide improvement priorities. Review OEE and PM compliance weekly; MTBF, MTTR, and defect rates monthly.

METRIC

CALCULATION

TARGET

Overall Equipment Effectiveness (OEE)

Availability x Performance x Quality

Target: >= 85%

Mean Time Between Failures (MTBF)

Total run time / Number of failures

Increase trend

Mean Time to Repair (MTTR)

Total repair time / Number of repairs

Decrease trend

PM Compliance Rate

PM completed on time / PM scheduled

Target: >= 90%

AM Compliance Rate

AM tasks completed / AM tasks scheduled

Target: >= 95%

Defect / Scrap Rate

Defective units / Total units produced

Decrease trend

Lost Time Incident Rate (LTIR)

Incidents x 200,000 / Hours worked

Target: 0

SIX BIG LOSSES QUICK REFERENCE

OEE CATEGORY

LOSS TYPE

DESCRIPTION

Availability

Equipment Breakdown

Unplanned stoppages caused by equipment failure — the most costly loss category.

Availability

Setup & Adjustment

Time lost during changeovers, warm-up periods, and equipment adjustments.

Performance

Idling & Minor Stops

Short, frequent interruptions that accumulate into significant lost production time.

Performance

Reduced Speed

Equipment running below its designed rate due to mechanical or material issues.

Quality

Process Defects

Scrap and rework generated during stable production due to equipment condition.

Quality

Startup Losses

Defects produced during startup or after changeovers before equipment stabilises.

PROGRAMME NOTES

This checklist is designed to be adapted to your facility's context, asset base, and organisational structure. Timings are indicative and may shift based on programme scale, resource availability, and current maturity.